## PCI DSS Audit Evidences
Sr.No. | Category | Evidences | Old List - Evidences | PCI DSS Reference | Status | QSA Comments
1 | Scoping | List of Locations in scope | List of Locations in scope | SCOPING | Done
2 | Scoping | List of Card Data Applications in scope | List of Card Data Applications in scope | SCOPING | Done
3 | Scoping | Asset Inventory (for all in scope systems) | Asset Inventory (for all in scope systems) | SCOPING | Pending - Missing Details | Refer to email shared on May 16 & 19
4 | Scoping | High Level Network Diagram for scoped environment | High Level Network Diagram for scoped environment | SCOPING | Done
5 | Scoping | Low Level Network Diagram for scoped environment | Low Level Network Diagram for scoped environment | SCOPING | Done
6 | Scoping | Card Data Flow / Process Flow Diagrams | Card Data Flow / Process Flow Diagrams | SCOPING | Pending - Missing Details | Refer to email shared on May 16 & 19
7 | Scoping | List of all Public/External Facing IP addresses in scope | List of all Public/External Facing IP addresses in scope | SCOPING | Done
8 | Scoping | PCI DSS Scope Review and Validation Document - Records of the annual PCI DSS scope review (every six months for service providers). - Documentation of any reviews conducted following significant changes to the in-scope environment. | PCI DSS Scope Review and Validation Document | SCOPING | Not Provided
9 | Pre-Scoping | Policies and Procedures covering implementation and maintenance of Network Security Controls |  | REQ 1 | Done
10 | Post-Scoping | Roles and Responsibilities Matrix/Document for all PCI DSS requirements | List of All VLANs or network segments in scope | All Requirements | Not Provided
11 | Post-Scoping | Few sampled network related change requests (ex. Ruleset addition, modification) | Few sampled network related change requests | REQ 1 | Not Provided
12 | Post-Scoping | Business Justification Document for use of services, protocols and ports on Network Security Controls (NSC) - e.g. firewalls, routers, etc. | Business Justification Document for use of services, protocols and ports on Network Security Controls (NSC) - e.g. firewalls, routers, etc. | REQ 1 | Not Provided
13 | Post-Scoping | Network Security Controls (Firewall) Ruleset Review Report (2 Compliant Bi-Annual Reports) | Network Security Controls (Firewall) Ruleset Review Report (2 Compliant Bi-Annual Reports) | REQ 1 | Pending - Missing Details | Firewall Rule Review_May 13 2024 SS Version - Not a valid report. Report doesn't fall under the current cert cycle
14 | Pre-Scoping | Provide details of how NSC configuration files are backed up and kept secured and consistent with the current active network configurations. | Provide a written explanation of how NSC configuration files are secured and are kept consistent with active network configurations. | REQ 1 | Not Provided
15 | Post-Scoping | Provide all inbound and outbound Access Control Lists (ACLs) for all in-scope networks in the form of system generated configuration files or snapshots from NSC console Kindly provide screenshot of Explicit Deny Rule from all NSC devices. | Provide all in-scope Access Control Lists (ACLs) in the form of system generated configuration files or snapshots from NSC console | REQ 1 | Not Provided
16 | Post-Scoping | If wireless technology is used to transmit cardholder data, provide all ACLs for transmission between wireless and wired networks | If wireless technology is used to transmit cardholder data, provide all ACLs for transmission between wireless and wired networks | REQ 1 | Not Provided
17 | Post-Scoping | Provide in-bound and outbound traffic logs on sample basis | Provide in-bound and outbound traffic logs on sample basis | REQ 1 | Done
18 | Post-Scoping | Screenshot of Anti-Spoofing setting on the NSCs (e.g. Firewall) in scope. | Screenshot of Anti-Spoofing setting on the NSCs (e.g. Firewall) in scope. | REQ 1 | Not Provided
19 | Post-Scoping | Provide screenshot to show stateful inspection enabled on external NSCs (e.g. firewalls) in scope. | Provide screenshot to show stateful inspection enabled on external NSCs (e.g. firewalls) in scope. | REQ 1 | Not Provided
20 | Post-Scoping | Provide evidence of personal/host-based firewall installed on user Laptops and Mobile Endpoints that connect to CDE and any other untrusted network (e.g. internet): - Hostname/IP of mobile endpoint - Version of firewall installed - Screenshot showing it cannot be disabled by user | Provide evidence of personal/host-based firewall installed on user Laptops and Mobile Endpoints in scope, including the following details: - Hostname/IP of mobile endpoint - Version of firewall installed - Screenshot showing it cannot be disabled by user | REQ 1 | Not Provided
21 | Post-Scoping | If a wireless access point is used, provide a screenshot that shows the following: - firmware version is the latest - strong encryption is implemented - vendor defaults are changed. | If a wireless access point is used, provide a screenshot that shows the following: - firmware version is the latest - strong encryption is implemented - vendor defaults are changed. | REQ 2 | Not Provided
22 | Pre-Scoping | Provide hardening documents for all in-scope technologies (e.g. windows, Linux, firewalls, routers, switches, etc) | Provide hardening documents for all in-scope technologies (e.g. windows, Linux, firewalls, routers, switches, etc) | REQ 2 | Pending - Missing Details | Switch - Missing DB - Missing Windows - Hardening of Win 2019 provided. Missing for 2016, 2022 Vmware - Missing
23 | Sample-Wise | Sample Wise: Provide screenshots of running services on sampled systems. Alternatively provide configuration scan reports for sampled systems. | Sample Wise: Provide screenshots of running services on sampled systems. Alternatively provide configuration scan reports for sampled systems. | REQ 2 | Not Provided
24 | Post-Scoping | For insecure services used in scoped environment, please provide details on additional controls in place to mitigate / reduce the risk exposure due to use of insecure services. | For insecure services used in scoped environment, please provide details on additional controls in place to mitigate / reduce the risk exposure due to use of insecure services. | REQ 2 | Not Provided
25 | Sample-Wise | Sample Wise: Provide screenshots of strong cryptography being used for transmission of credentials, etc. | Sample Wise: Provide screenshots of strong cryptography being used for transmission of credentials, etc. | REQ 2 | Not Provided
26 | Post-Scoping | Provide the Cardholder Data Matrix that includes cardholder data components (including SAD) being stored, protection mechanism, retention period, deletion method, etc. | Provide the Cardholder Data Matrix that includes cardholder data components being stored, protection mechanism, retention period, deletion method, etc | REQ 3 | Not Provided
27 | Post-Scoping | ONLY If Sensitive Authentication Data (SAD) is being Stored: - Provide details of how SAD is encrypted using strong cryptography - Provide Documented Business Justification for storage of SAD - Provide details of how SAD is securely deleted once retention period is lapsed | ONLY If Sensitive Authentication Data (SAD) is being Stored: - Provide Documented Business Justification for storage of SAD - Provide the details of the technical controls used to secure the SAD in storage | REQ 3 | Not Provided
28 | Post-Scoping | If Hashing is used for protecting stored PAN, provide the following: - Details of the cryptographic hashing algorithm in use - Key Management Procedure for managing cryptographic keys used in the hashing algorithm |  | REQ 3 | Not Provided
29 | Post-Scoping | Provide evidence of card data scans or manual process for identification of cardholder data on system components in scope | Provide evidence of card data scans or manual process for identification of cardholder data on system components in scope | REQ 3 | Not Provided
30 | Pre-Scoping | Data Encryption Policy / Standard document | Data Encryption Policy / Standard document | REQ 3 | Done
31 | Pre-Scoping | Data Retention and Disposal Policy |  | REQ 3 | Done
32 | Post-Scoping | Key Management and Encryption Process Document which includes the following: - Details of DEK and KEK strength and key-length - DEK and KEK secure key generation process - Screenshots of DEK and KEK generation functions - Location of encrypted DEK and KEK storage - Screenshots of encrypted DEK and KEK (at rest) - Location of encrypted PAN/SAD storage - Screenshot of encrypted PAN/SAD storage - Encryption and Decryption process description (with process flow diagrams) - Screenshots from code showing encryption/decryption functions - Key Custodian Forms for both DEK and KEK - Key Replacement / Rotation process (including retiring or archival process) - List of users who have access to cleartext cryptographic key components | Key Management and Encryption Process Document which includes the following: - Details of DEK and KEK strength and key-length - DEK and KEK secure key generation process - Screenshots of DEK and KEK generation functions - Location of encrypted DEK and KEK storage - Screenshots of encrypted DEK and KEK (at rest) - Location of encrypted PAN storage - Screenshot of encrypted PAN storage - Encryption and Decryption process description (with process flow diagrams) - Screenshots from code showing encryption/decryption functions - Key Custodian Forms for both DEK and KEK - Key Replacement / Rotation process (including retiring or archival process) | REQ 3 | Not Provided
33 | Post-Scoping | If Disk Encryption is being used, kindly provide details of the Disk Encryption mechanism in use. Also provide details of additional encryption mechanisms in use along with the disk encryption. | If Disk Encryption is being used, kindly provide details of the Disk Encryption mechanism in use. Also provide details of additional encryption mechanisms in use along with the disk encryption. | REQ 3 | Not Provided
34 | Post-Scoping | Provide below sample logs from Application server, DB server & payment applications to validate that full track data or PIN or PIN block is not stored after authorization- • Incoming transaction data • All logs (for example, transaction, history, debugging, error) • History files • Trace files • Several database schemas • Database contents | Provide below sample logs from Application server, DB server & payment applications to validate that full track data or PIN or PIN block is not stored after authorization- • Incoming transaction data • All logs (for example, transaction, history, debugging, error) • History files • Trace files • Several database schemas • Database contents | REQ 3 | Not Provided
35 | Post-Scoping | If Remote access technology is being used to access Cardholder Data (PAN), provide the following: - Technical controls in place for preventing the copy or relocation of PAN for unauthorized personnel - A list of personnel with permission to copy and/or relocate PAN along with the documented, explicit authorization and legitimate, defined business need. |  | REQ 3 | Pending - Missing Details | Evidence required - A list of personnel with permission to copy and/or relocate PAN along with the documented, explicit authorization and legitimate, defined business need.
36 | Post-Scoping | Provide the business justification for display of full card numbers on front-end screens or backend files/systems | Provide the business justification for display of full card numbers on front-end screens or backend files/systems | REQ 3 | Not Provided
37 | Post-Scoping | Screenshots of all card number displays on front end screens and back-end files/systems | Screenshots of all card number displays on front end screens and back-end files/systems | REQ 3 | Not Provided
38 | Post-Scoping | Data deletion mechanism records (evidences showing secure card data deletion for data exceeding the defined retention period) | Data deletion mechanism records (evidences showing secure card data deletion for data exceeding the defined retention period) | REQ 3 | Not Provided
39 | Post-Scoping | For Cardholder data transmission on public networks (internet) please provide evidence of secure cryptography in use. | For Cardholder data transmission on public networks (internet) please provide evidence of secure cryptography in use. | REQ 4 | Pending - Incorrect Evidence | Evidence of use of HTTPS, TLS 1.2 or above required
40 | Post-Scoping | List of certificates and trusted keys used for trainsmission of PAN along with details of validity, expiry date and revocation status for each. |  | REQ 4 | Not Provided
41 | Post-Scoping | Provide Sample transmission logs for cardholder data transmission over public networks | Provide Sample transmission logs for cardholder data transmission over public networks | REQ 4 | Not Provided
42 | Post-Scoping | If PAN is sent using end-user messaging technology, please provide details of use of encryption mechanism to protect the PAN. | If PAN is sent using end-user messaging technology, please provide details of use of encryption mechanism to protect the PAN. | REQ 4 | Not Provided
43 | Pre-Scoping | Anti-Malware management policy/procedure | Anti-Malware management policy/procedure | REQ 5 | Done
44 | Sample-Wise | Sample Wise: Provide following evidence of Anti Malware solution from sampled endpoints and servers: - Anti-Malware solution actively running on system - Version of Anti malware client on systems - Anti-malware cannot be disabled by normal users - Date and Time of Last Scan on system - Data and time of last signature update from anti-malware server | Sample Wise: Provide following evidence of Anti Malware solution from sampled endpoints and servers: - Anti-Malware solution actively running on system - Version of Anti malware client on systems - Anti-malware cannot be disabled by normal users - Date and Time of Last Scan on system - Data and time of last signature update from anti-malware server | REQ 5 | Not Provided
45 | Post-Scoping | From Anti-malware server : provide the following screenshots: - Version of Anti Malware from central console - List of all systems integrated with Anti Malware\ server - Anti Malware signature version - Anti Malware update frequency - Anti Malware scan frequency - Anti Malware logs - Anti Malware log retention settings | From Anti-malware server : provide the following screenshots: - Version of Anti Malware from central console - List of all systems integrated with Anti Malware\ server - Anti Malware signature version - Anti Malware update frequency - Anti Malware scan frequency - Anti Malware logs - Anti Malware log retention settings | REQ 5 | Not Provided
46 | Post-Scoping | IF Continuous Behavior Analysis is being used for identifying malware threats, please provide: - Settings showcasing the continuous behavior analysis feature on the said solution - Or, vendor documentation showing continuous behavior analysis is carried out by default | IF Continuous Behavior Analysis is being used for identifying malware threats, please provide: - Settings showcasing the continuous behavior analysis feature on the said solution - Or, vendor documentation showing continuous behavior analysis is carried out by default | REQ 5 | Not Provided
47 | Post-Scoping | Provide evidence that: - Removable media is scanned when inserted/mounted/connected OR - Conducts continuous behavioral analysis of the system, once removable media is inserted/mounted/connected to the system |  | REQ 5 | Done
48 | Post-Scoping | IF email server or email service is being used in either CDE or Non-CDE network, provide evidence of: - Processes and automated mechanisms in place to detect and protect personnel against "Phishing attacks" |  | REQ 5 | Not Provided
49 | Pre-Scoping | Provide evidence that any security alerts or threat notifications are analyzed against the asset/application inventory and a risk ranking process applied to the alerts. | Provide evidence that any security alerts or threat notifications are analyzed against the asset/application inventory and a risk ranking process applied to the alerts. | REQ 6 | Pending - Incorrect Evidence | Please provide sample alert evidence
50 | Sample-Wise | Sample Wise: Provide screenshots showing latest patch / version update for all sampled systems | Sample Wise: Provide screenshots showing latest patch / version update for all sampled systems | REQ 6 | Not Provided
51 | Pre-Scoping | SDLC or Application Development Policy document | SDLC or Application Development Policy document | REQ 6 | Done
52 | Post-Scoping | List of users configured on all in-scope applications which have exposure of cardholder data | List of users configured on all in-scope applications which have exposure of cardholder data | REQ 6 | Not Provided
53 | Post-Scoping | Evidence showing secure code review carried out of all in-scope applications (provide secure code review report) | Evidence showing secure code review carried out of all in-scope applications (provide secure code review report) | REQ 6 | Not Provided
54 | Post-Scoping | Evidence showing the segregation between: - Dev, UAT and Production Environment - Dev, UAT and Production Users - Encryption Keys used in UAT must be different from Prod | Evidence showing the segregation between: - Dev, UAT and Production Environment - Dev, UAT and Production Users | REQ 6 | Not Provided
55 | Post-Scoping | Provide the evidence of test data generation process used in pre-production environments. |  | REQ 6 | Not Provided
56 | Post-Scoping | Inventory of applications and software (third-party, bespoke or in-house developed) |  | REQ 6 | Not Provided
57 | Post-Scoping | Kindly provide the following: - An inventory of all scripts with written business or technical justification as to why each is necessary - Evidence of method implemented to confirm that each script is authorized. - Evidence of method implemented to assure the integrity of each script. |  | REQ 6 | Not Provided
58 | Post-Scoping | 1. Provide Change Management Policy 2. Provide evidence for following change requests: - Sample 2 application changes - Sample 2 system level changes (patch update, etc) Please ensure the CRs contain the following at a minimum: - Change description and date - Change approver information - Change impact information - Change testing details - Change back - out plan | 1. Provide Change Management Policy 2. Provide evidence for following change requests: - Sample 2 application changes - Sample 2 system level changes (patch update, etc) Please ensure the CRs contain the following at a minimum: - Change description and date - Change approver information - Change impact information - Change testing details - Change back - out plan | REQ 6 | Not Provided
59 | Post-Scoping | Provide Secure Coding Guidelines. Also provide evidence that developers are trained annually for secure coding practices. Please provide following: - Developer Training record - Secure coding training material | Provide Secure Coding Guidelines. Also provide evidence that developers are trained annually for secure coding practices. Please provide following: - Developer Training record - Secure coding training material | REQ 6 | Not Provided
60 | Post-Scoping | If WAF is used, provide details of WAF along with supporting screenshots: - Version - Logs - Protection against OWASP Top 10 Attacks - Alerts and monitoring records | If WAF is used, provide details of WAF along with supporting screenshots: - Version - Logs - Protection against OWASP Top 10 Attacks | REQ 6 | Not Provided
61 | Pre-Scoping | Logical Access Control Policy | Logical Access Control Policy | REQ 7 | Done
62 | Sample-Wise | Sample Wise: Provide screenshots showing user list on all sampled systems | Sample Wise: Provide screenshots showing user list on all sampled systems | REQ 7 | Not Provided
63 | Post-Scoping | Provide business justification and approval records for the use of group, shared, or generic accounts |  | REQ 7 | Not Provided
64 | Post-Scoping | Provide sample user creation/deletion/modification records | Provide sample user creation/deletion/modification records | REQ 7 | Done
65 | Pre-Scoping | Provide evidence of access rights removal for 3 to 4 user employment termination | Provide evidence of access rights removal for 3 to 4 user employment termination | REQ 7 | Not Provided
66 | Post-Scoping | User access review reports or evidences (must be conducted every 6 months) including: - Review of all user accounts and related access privileges, including third-party/vendor accounts - Acknowledgement from management that all access remains appropriate | User access review reports or evidences (must be conducted every 6 months) | REQ 7 | Not Provided
67 | Post-Scoping | Provide evidence of review of all access by application and system accounts and related access privileges including the following: - Such access is reviewed periodically - The application/system access remains appropriate for the function being performed. - Records showing that any inappropriate access is addressed. - Management acknowledges that access remains appropriate | User access review reports or evidences (must be conducted every 6 months) | REQ 7 | Not Provided
68 | Post-Scoping | Provide an inventory of vendors that are provided remote access to your organization. For each vendor, please provide - Procedure for providing access only when needed - Access activity monitoring reports | Provide an inventory of vendors that are provided remote access to your organization. For each vendor, please provide - Procedure for providing access only when needed - Access activity monitoring reports | REQ 7 | Not Provided
69 | Sample-Wise | Sample Wise: Provide screenshots showing the password policy, account lockout policy and idle session timeout on all sampled systems | Sample Wise: Provide screenshots showing the password policy, account lockout policy and idle session timeout on all sampled systems | REQ 8 | Not Provided
70 | Sample-Wise | Sample Wise: Provide screenshots showing the that encryption mechanism is used for storage and transmission of passwords on all sampled systems | Sample Wise: Provide screenshots showing the that encryption mechanism is used for storage and transmission of passwords on all sampled systems | REQ 8 | Not Provided
71 | Post-Scoping | Provide one sample per platform of recent password reset requests/forms for users. | Provide one sample per platform of recent password reset requests/forms for users. | REQ 8 | Not Provided
72 | Post-Scoping | For one sample per platform provide the screenshot of the setting which forces the user to change the password after the first logon. | For one sample per platform provide the screenshot of the setting which forces the user to change the password after the first logon. | REQ 8 | Not Provided
73 | Post-Scoping | Evidence showing Muti-Factor Authentication for all non-console access to CDE is enabled. | Evidence showing Muti-Factor Authentication for all non-console access to CDE is enabled. | REQ 8 | Not Provided
74 | Post-Scoping | Evidence showing that Multi-Factor Authentication is used for all remote access into the CDE. Also provide a list of all internal and external users with remote access to CDE. | Evidence showing that Multi-Factor Authentication is used for all remote access into the CDE. Also provide a list of all internal and external users with remote access to CDE. | REQ 8 | Not Provided
75 | Post-Scoping | Provide Evidence that MFA systems are implemented as follows: - The MFA system is not susceptible to replay attacks. - MFA systems cannot be bypassed by any users, including administrative users unless specifically documented, and authorized by management on an exception basis, for a limited time period. - At least two different types of authentication factors are used. - Success of all authentication factors is required before access is granted. |  | REQ 8 | Not Provided
76 | Post-Scoping | If accounts used by systems or applications are used for interactive login, provide the following evidence: - Documentation showing that interactive use is prevented unless required for an exceptional circumstance. - Evidence that interactive use is limited to the time needed for the exceptional circumstance. - Documented business justification for interactive use. - Management approval records. - Evidence showing that Individual user identity is confirmed before access to account is granted. - Sample logs that shows every action taken is attributable to an individual user. |  | REQ 8 | Not Provided
77 | Post-Scoping | Provide configuration evidence showing passwords/passphrases for any application and system accounts that is used for interactive login are not hardcoded in scripts, configuration/property files, or bespoke/custom source code. |  | REQ 8 | Not Provided
78 | Post-Scoping | Evidence showing re-authentication is required for all remote sessions if it remains idle for more than the defined time interval as per remote access policy | Evidence showing re-authentication is required for all remote sessions if it remains idle for more than the defined time interval as per remote access policy | REQ 8 | Not Provided
79 | Post-Scoping | For all the databases in scope provide the output screenshot of current active connections. | For all the databases in scope provide the output screenshot of current active connections. | REQ 8 | Not Provided
80 | Pre-Scoping | Provide evidence of guidance provided to customers for the following: - Guidance to change password periodically or when suspected to be compromised |  | REQ 8 | Not Provided
81 | Post-Scoping | Provide the following for all physical locations in scope: - Sample records from physical access control system (such as a badge system). Evidence showing 90 days of retention for physical access control logs - Screenshot of video cameras Recordings. Evidence showing 90 days of retention for all camera recordings - List of users created on access control system (such as a badge system and CCTV console) for administrative access | Provide the following for all physical locations in scope: - Sample records from physical access control system (such as a badge system). Evidence showing 90 days of retention for physical access control logs - Screenshot of video cameras Recordings. Evidence showing 90 days of retention for all camera recordings - List of users created on access control system (such as a badge system and CCTV console) for administrative access | REQ 9 | Not Provided
82 | Post-Scoping | Provide two samples of user access creation and deletion forms/tickets from the last six months for the following: - Physical access allocation to the sensitive area is authorized and as per individual's job function. - Timely removal of physical access upon termination of user. | Provide two samples of user access creation and deletion forms/tickets from the last six months for the following: - Physical access allocation to the sensitive area is authorized and as per individual's job function. - Timely removal of physical access upon termination of user. | REQ 9 | Not Provided
83 | Post-Scoping | Visitor Management Evidences: 1. Provide evidence of visitor log book (physical or digital) including: - Log book for visitor access to facility - Log book for visitor access to server room (if applicable) 2. Evidence of visitor badges (provide one or two sample visitor badge), showing the contents on the badge and the color of the badge. 3. Provide information as to how you differentiate between employees and visitors in the premises. | Visitor Management Evidences: 1. Provide evidence of visitor log book (physical or digital) including: - Log book for visitor access to facility - Log book for visitor access to server room (if applicable) 2. Evidence of visitor badges (provide one or two sample visitor badge), showing the contents on the badge and the color of the badge. 3. Provide information as to how you differentiate between employees and visitors in the premises. | REQ 9 | Not Provided
84 | Pre-Scoping | Physical and environmental security Policy | Physical and environmental security Policy | REQ 9 | Done
85 | Post-Scoping | This is applicable only if physical media is used for backups of covered information and stored offsite. Provide evidence that a physical security review has been performed on the backup facility. | This is applicable only if physical media is used for backups of covered information and stored offsite. Provide evidence that a physical security review has been performed on the backup facility. | REQ 9 | Not Provided
86 | Post-Scoping | This is applicable only if physical media is used to store covered information. Provide the following: - Full media inventory - A sample of 5 inbound and outbound media movement records (including information such as date/time of movement, approver name, delivery method) from last six months | This is applicable only if physical media is used to store covered information. Provide the following: - Full media inventory - A sample of 5 inbound and outbound media movement records (including information such as date/time of movement, approver name, delivery method) from last six months | REQ 9 | Not Provided
87 | Post-Scoping | Provide the physical media destruction procedure and a sample of media destruction records from within the last year. | Provide the physical media destruction procedure and a sample of media destruction records from within the last year. | REQ 9 | Not Provided
88 | Post-Scoping | If Point of Sale (POS) devices are in scope: Provide up-to-date list of point of sale devices (card-reading devices and terminals) with information that includes: - Make and model of device. - Location of the device (for example, the address of the site or facility where the device is located). - Device serial number or another method of unique identification. | If Point of Sale (POS) devices are in scope: Provide up-to-date list of point of sale devices (card-reading devices and terminals) with information that includes: - Make and model of device. - Location of the device (for example, the address of the site or facility where the device is located). - Device serial number or another method of unique identification. | REQ 9 | Not Provided
89 | Post-Scoping | If Point of Sale (POS) devices are in scope: Documented procedures that outline the process for inspection for tampering. - The material used for training personnel for inspection. - Records showing that personnel has been trained. - A sample of 3 records from different retail locations showing the schedule of inspection. | If Point of Sale (POS) devices are in scope: Documented procedures that outline the process for inspection for tampering. - The material used for training personnel for inspection. - Records showing that personnel has been trained. - A sample of 3 records from different retail locations showing the schedule of inspection. | REQ 9 | Not Provided
90 | Post-Scoping | Cardholder data on paper copies: In case of paper copies containing cardholder data, provide evidence of shredding after retention period is over. | Cardholder data on paper copies: In case of paper copies containing cardholder data, provide evidence of shredding after retention period is over. | Req 9 | Not Provided
91 | Sample-Wise | Sample Wise: Provide screenshots showing the audit log policy setting on all sampled systems | Sample Wise: Provide screenshots showing the audit log policy setting on all sampled systems | REQ 10 | Not Provided
92 | Post-Scoping | Provide actual event logs for each of the technology / platforms in the PCI DSS scope for the following events: - All individual user accesses to cardholder data - All actions taken by any individual with root or administrative privileges - Access to all audit trails - Invalid logical access attempts - Use of and changes to identification and authentication mechanisms—including but not limited to creation of new accounts and elevation of privileges—and all changes, additions, or deletions to accounts with root or administrative privileges - Initialization, stopping, or pausing of the audit logs - Creation and deletion of system-level objects Sample logs must show that below entries are captured- • User identification • Type of event • Date and time • Success or failure indication • Origination of event | Provide actual event logs for each of the technology / platforms in the PCI DSS scope for the following events: - All individual user accesses to cardholder data - All actions taken by any individual with root or administrative privileges - Access to all audit trails - Invalid logical access attempts - Use of and changes to identification and authentication mechanisms—including but not limited to creation of new accounts and elevation of privileges—and all changes, additions, or deletions to accounts with root or administrative privileges - Initialization, stopping, or pausing of the audit logs - Creation and deletion of system-level objects Sample logs must show that below entries are captured- • User identification • Type of event • Date and time • Success or failure indication • Origination of event | REQ 10 | Not Provided
93 | Sample-Wise | Sample Wise: Provide screenshots showing the NTP setting on all sampled systems including the following: - Device being used as the central NTP server along with the NTP version number - Setting/Screenshot showing sync between NTP server and external time source - Access control list for NTP server | Sample Wise: Provide screenshots showing the NTP setting on all sampled systems including the following: - Device being used as the central NTP server along with the NTP version number - Setting/Screenshot showing sync between NTP server and external time source - Access control list for NTP server | REQ 10 | Not Provided
94 | Post-Scoping | From the log server or appliance, showcase evidence that all centralized logs are protected by File Integrity Monitoring | From the log server or appliance, showcase evidence that all centralized logs are protected by File Integrity Monitoring | REQ 10 | Pending - Incorrect Evidence | Evidence of how the logs are protected not provided in the evidence file
95 | Post-Scoping | Provide evidence of daily log review / log alerts generated by automated mechanism (SIEM) being monitored. | Provide Evidence of daily log review / log alerts being monitored. | REQ 10 | Done
96 | Post-Scoping | Evidence of 1 year logs are retained in log server. | Evidence of 1 year logs are retained in log server. | REQ 10 | Not Provided
97 | Post-Scoping | Sample reports/alerts from FIM. | Sample reports/alerts from FIM. | REQ 10 | Not Provided
98 | Post-Scoping | Sample tickets of failure of Security Controls Systems (Ex. Network security controls, IDS/IPS FIM, Anti-malware solutions, Physical access controls, Logical access controls, Audit logging mechanisms, Segmentation controls) |  | REQ 10 | Not Provided
99 | Pre-Scoping | Guidelines for wireless scanning | Guidelines for wireless scanning | REQ 11 | Not Provided
100 | Post-Scoping | Wireless scan reports for last 4 quarters | Wireless scan reports for last 4 quarters | REQ 11 | Not Provided
101 | Pre-Scoping | Security incident management procedure | Security incident management procedure | REQ 11 | Done
102 | Post-Scoping | Evidence of internal vulnerability scans performed via authenticated scanning, including: - A list of systems that are unable to accept credentials for authenticated scanning, along with documentation explaining why. - Documentation demonstrating that sufficient privileges are used for systems that accept credentials for scanning. | Internal VA report for last 4 quarters | REQ 11 | Not Provided
103 | Post-Scoping | Report for ASV scans for last 4 quarters | Report for ASV scans for last 4 quarters | REQ 11 | Not Provided
104 | Post-Scoping | Internal PT report (Application layer and Network layer) | Internal PT report (Application layer and Network layer) | REQ 11 | Not Provided
105 | Post-Scoping | External PT report (Application layer and Network layer) | External PT report (Application layer and Network layer) | REQ 11 | Not Provided
106 | Post-Scoping | Segmentation PT report (2 reports for service providers) | Segmentation PT report (2 reports for service providers) | REQ 11 | Not Provided
107 | Pre-Scoping | Documented methodology document for penetration testing | Documented methodology document for penetration testing | REQ 11 | Not Provided
108 | Post-Scoping | Provide evidence of the following from all IDS/IPS implemented: - Location on network - Version number - Signatures - Alerting emails - Follow up to alerts - sample tickets of detection, alert or/prevention, of covert malware communication channels attack. | Provide evidence of the following from all IDS/IPS implemented: - Location on network - Version number - Signatures - Alerting emails - Follow up to alerts | REQ 11 | Not Provided
109 | Post-Scoping | Provide the following evidence for FIM: - FIM version installed - Files being monitored by FIM - Alerting emails - Follow up to alerts | Provide the following evidence for FIM: - FIM version installed - Files being monitored by FIM - Alerting emails - Follow up to alerts | REQ 11 | Not Provided
110 | Post-Scoping | Provide the following evidence of change- and tamper-detection mechanism used on payment pages: - Configuration of change- and tamper-detection mechanism. - Alerts - Weekly review OR frequency defined as per targeted risk analysis |  | REQ 11 | Not Provided
111 | Pre-Scoping | Information security policy. | Information security policy. | REQ 12 | Done
112 | Pre-Scoping | Risk Management Policy/Framework and Procedure | Risk Management Policy/Framework and Procedure | REQ 12 | Done
113 | Post-Scoping | Provide Targetted Risk Analysis: - List down all periodic activities to be covered as part of TRA - Frequency of periodic training for incident response personnel - Frequency of periodic POI device inspections and the type of inspections performed - Frequency of periodic log reviews for all other system components. - Frequency of periodic review of change- and tamper-detection mechanism | Provide Risk Assessment Report/Risk Register containing: - Risk assessment methodology - Formalized risk assessment report - Risk acceptance criteria - Risk treatment plan | REQ 12 | Not Provided
114 | Pre-Scoping | Acceptable usage policy. | Acceptable usage policy. | REQ 12 | Done
115 | Pre-Scoping | Remote access policy | Remote access policy | REQ 12 | Done
116 | Pre-Scoping | Security incident management procedure / incident response plan | Security incident management procedure / incident response plan | REQ 12 | Done
117 | Post-Scoping | Provide Incident handling training records for team with security breach response responsibilities. | Provide Incident handling training records for team with security breach response responsibilities. | REQ 12 | Not Provided
118 | Post-Scoping | Provide evidence of incident response procedures for detecting and responding to PAN found outside the CDE, including: - Processes for retrieving, securely deleting, or migrating the PAN. - Steps to identify if sensitive authentication data is stored with PAN. - Investigation of how and why the PAN was improperly stored. - Remediation of data leaks or process gaps identified. Also, provide a sample incident tickets demonstrating the handling of such incidents. |  | REQ 12 | Not Provided
119 | Post-Scoping | Sample Security incident tickets | Sample Security incident tickets | REQ 12 | Not Provided
120 | Pre-Scoping | Organization Chart showcasing the information security function within the organization | Organization Chart showcasing the information security function within the organization | REQ 12 | Not Provided
121 | Pre-Scoping | Provide documentation of the internal review process conducted after significant changes to the organizational structure. Also, provide the following evidence: - Results being communicated to executive management, such as meeting minutes or reports. - Documented review of the impact to PCI DSS scope and applicability of controls. |  | REQ 12 | Not Provided
122 | Pre-Scoping | HR background verification policy Provide a sample of 10 employee background checks records from last year. | HR background verification policy Provide a sample of 10 employee background checks records from last year. | REQ 12 | Not Provided
123 | Pre-Scoping | Provide information security awareness material used for user training. Also, provide the following evidence: - Training material/program review records (at least once every 12 months) - The training materials contents that covers topic related to Phishing and related attacks, social engineering, acceptable use of end-user technologies |  | REQ 12 | Done
124 | Pre-Scoping | Provide information security awareness material used for user training. Also, provide 5 sample training attendance records from last one year period for: - existing employees - recently hires - contractors | Provide information security awareness material used for user training. Also, provide 5 sample training attendance records from last one year period for: - existing employees - recently hires - contractors | REQ 12 | Done
125 | Pre-Scoping | Provide evidence of the review of hardware and software technologies in use, conducted at least annually, including: - Analysis confirming that technologies continue to receive timely security fixes from vendors. - Analysis ensuring the technologies support the entity’s PCI DSS compliance. - Documentation of any industry announcements or trends, including vendor 'end of life' plans for technologies. - A remediation plan, approved by senior management, for outdated technologies or those with announced 'end of life' plans. | HR Policy (including onboarding and off-boarding procedures) | REQ 12 | Not Provided
126 | Pre-Scoping | Provide evidence of the documentation and review of cryptographic cipher suites and protocols, conducted at least annually, including: - An up-to-date inventory of all cryptographic cipher suites and protocols in use, detailing their purpose and where they are used. - Active monitoring of industry trends regarding the viability of these cryptographic technologies. - A documented plan to respond to anticipated changes or vulnerabilities in cryptographic technologies. | Relieving records for the sampled employees who left the organization in last 1 year | REQ 12 | Not Provided
127 | Pre-Scoping | List of service providers in PCI DSS scope | List of service providers in PCI DSS scope | REQ 12 | Not Provided
128 | Post-Scoping | For all in scope third party service providers, provide their PCI DSS AOC certificates showcasing their compliance status | For all in scope third party service providers, provide their PCI DSS AOC certificates showcasing their compliance status | REQ 12 | Not Provided
129 | Post-Scoping | Third party due diligence checklist | Third party due diligence checklist | REQ 12 | Not Provided
130 | Post-Scoping | Provide a sample written acknowledgment (contractual) that outlines that service providers are responsible for the security of your customer's data | Provide a sample written acknowledgment (contractual) that outlines that service providers are responsible for the security of your customer's data | REQ 12 | Done
131 | Post-Scoping | Updated Project PCI DSS certification charter | Updated Project PCI DSS certification charter | REQ 12 | Done
132 | Post-Scoping | Evidence of quarterly compliance reviews to ensure: • Daily log reviews • Firewall rule-set reviews • Applying configuration standards to new systems • Responding to security alerts • Change management processes | Evidence of quarterly compliance reviews to ensure: • Daily log reviews • Firewall rule-set reviews • Applying configuration standards to new systems • Responding to security alerts • Change management processes | REQ 12 | Not Provided
133 | Pre-Scoping | Acknowledgement from staff at least annually that they have read and understood the security policy and procedures. | Acknowledgement from staff at least annually that they have read and understood the security policy and procedures. | REQ 12 | Done